## Requirement Traceability Matrix
Requirements Traceability Matrix for |  | Rules Based Decision Aid Framework |  |  | Version 1.0
|  |  | Design | Verification
| Solution Requirements (User Stories) | Description | Design Document Reference | Test or Verification Reference | Comments
| Trello PBI #48 | The user has the ability to import and parse data in the RBDE from an external file | Refer to the Design doc v1.0 pages 5 and 9 | Development, unit and integration tests are still in progress.
| Trello PBI #40 | The user can take imported and parsed data to create a data object | Refer to the Design doc v1.0 pages 5 and 9 | Development, unit and integration tests are still in progress.
| Trello PBI #84 | The user has access to a simple GUI in order to do Drool operations | Refer to the GUI mockup in the design document v1.0 on page 6 | Development, unit and integration tests are still in progress.
| Trello PBI #87 | The user should be able to dynamically create new rules | Refer to the Design doc v1.0 page 5: "Rule Object/Drools drl creation module" | Refer to PBI #76 | Can also refer to PBI #'s 85 and 76, since they were used to help with this
| Trello PBI #76 | The user should have a complete and fully functional Rules class used to help make new rules | Refer to pages 5, 8 and 9 of the Design doc v1.0: "Rule Object/Drools drl creation module", "Rule", and "RuleCollectionService" respectively | Refer to 'ActionTester' and 'ConditionalTester' on the master branch on github under the 'testing folder' | Link to the Wolf Team's github page: https://github.com/TestPlan/rules-based-decision-engine.git
| Trello PBI #85 | The user should have the abililty to create a drl file with any number of constraints in the condition part of the rule. | Refer to page 5 of the Design doc v1.0: "Rule Object/Drools drl creation module" | Development and unit testing are still in progress | Can refer to PBI's #91 and #92 on Trello
| Trello PBI # 82 | The user should have the ability to store and retrieve a rule object via serialization and deserialization | Refer to page 9 of the Design doc v1.0: "SerializationService" | Refer to 'SerializationTest' on the master branch of github, under the 'testing' folder | Link to the Wolf Team's github page: https://github.com/TestPlan/rules-based-decision-engine.git
| Trello PBI #39 | The user should be able to associate sets of data with rules | Refer to pages 5 and 7 in the Design doc v1.0: "Data Association Module" and "Rule Activation" respectively | Refer to 'RuleActivationTest' on the master branch on github under the 'testing' folder | Link to the Wolf Team's github page: https://github.com/TestPlan/rules-based-decision-engine.git
| Trello PBI #69 | The user has the ability to import data from a csv file and store that data into an object | Refer to pages 5 and 9 in the Design doc v1.0: "Data Import Module" and "FileReaderService" Respectively | Development and Integration Tests are still in progress
| Trello PBI #68 | The user has the ability to import data from a JSON file and store that data into an object | Refer to pages 5 and 9 in the Design doc v1.0: "Data Import Module" and "FileReaderService" Respectively | Development and Integration Tests are still in progress

## RTM Approvers & Version Histroy
Version | Version Date | Revisions
1 | 2016-12-04 | Enter reference to solution version release or RFC. Specific changes to the Matrix sheet do not need to be recorded.